## RISK
RIESGO
RIESGO ES LA PROBABILIDAD DE UN EVENTO INDESEABLE Y EL EFECTO DE LA CONSECUENCIA DE DICHO EVENTO
LA FORMULA MAS SIMPLE PARA SU CALCULO ES LA SIGUIENTE
R = Po x Mf
PO
Po = PROBABILIDAD DE OCURRENCIA |  |  | 4 | 4 | 8 | 12 | 16
Mf = MAGNITUD DEL DAÑO (IMPACTO DEL EVENTO) |  |  | 3 | 3 | 6 | 9 | 12
|  |  | 2 | 2 | 4 | 6 | 8
|  |  | 1 | 1 | 2 | 3 | 4
PARA CALCULAR LOS VALORES SE DEBERÁN DE TOMAR LAS SIGUIENTES ESCALAS |  |  |  | 1 | 2 | 3 | 4 | MF
ESCALA | PO | MF
1 | POCO PROBABLE | LEVE
2 | PROBABLE | MODERADO |  | INACEPTABLE |  | 1
3 | FRECUENTE | ALTO | RIESGO= | IMPORTANTE |  | 2
4 | MUY FRECUENTE | CATASTROFICO |  | MODERADO |  | 3
|  |  |  | TOLERABLE |  | 4

## MATRIZ
MATRIS DE RIESGOS
|  | RISK AREA | KIND OF RISK | ROLE | Po | Mf | RISK SCALE | PLAN OF PREVENTION | ACTION PLAN | COST
1 | 1 | HUMAN RESOURCES RISK | NON-ATTENDANCE | ADMINISTRATOR | 1 | 4 | 4 | Attendance bonus | Delegate activities to the analyst
2 | 2 | HUMAN RESOURCES RISK | NON-ATTENDANCE | ANALYST | 1 | 3 | 3 | Attendance bonus | Delegate activities to the administrator
| 3 | HUMAN RESOURCES RISK | NON-ATTENDANCE | DESIGNER | 2 | 2 | 4 | Attendance bonus | Delegate activities to the tester
3 | 4 | HUMAN RESOURCES RISK | NON-ATTENDANCE | PROGRAMMER | 2 | 4 | 8 | Attendance bonus | Delegate activities to the analyst | 15000
4 | 5 | HUMAN RESOURCES RISK | NON-ATTENDANCE | DATA BASE | 1 | 4 | 4 | Attendance bonus | Delegate activities to the programmer
| 6 | HUMAN RESOURCES RISK | NON-ATTENDANCE | TESTER | 1 | 2 | 2 | Attendance bonus | Delegate activities to the analyst
| 7 | HUMAN RESOURCES RISK | NON-ATTENDANCE | CLERK | 1 | 1 | 1 | Attendance bonus | Delegate activities to the tester
5 | 8 | HUMAN RESOURCES RISK | NON-ATTENDANCE | TECHNICAL SUPPORT | 1 | 3 | 3 | Attendance bonus | Delegate activities to the clerk
| 9 | HUMAN RESOURCES RISK | NON-ATTENDANCE | ADMINISTRATIVES | 3 | 2 | 6 | Attendance bonus | Delegate activities to the analyst
| 10 | HUMAN RESOURCES RISK | CONFLICTS |  | 2 | 3 | 6 | Work meetings and problem solving | Emergency meeting for conflict resolution
| 11 | HUMAN RESOURCES RISK | SABOTAGE |  | 2 | 4 | 8 | Responsibility matrix | Delegate role activities to another role | 30000
| 12 | HUMAN RESOURCES RISK | LACK OF KNOWLEDGE |  | 3 | 3 | 9 | Trainings | Hire an expert to train in whatever is required | 15000
6 | 13 | HUMAN RESOURCES RISK | INFORMATION LEAK |  | 1 | 4 | 4 | Confidentiality agreements | Take legal action
7 | 14 | HUMAN RESOURCES RISK | INTERNAL ROBBERY |  | 1 | 4 | 4 | Hire someone new team members | Take legal action
8 | 15 | HUMAN RESOURCES RISK | LOW PERFORMANCE |  | 2 | 3 | 6 | Compromise agreements with the staff | Use coaching
9 | 16 | FACILITIES RISK | FIRE |  | 1 | 4 | 4 | Safety signs and fire extinguishers | Follow legal measures
10 | 17 | FACILITIES RISK | EARTHQUAKE |  | 1 | 4 | 4 | Safety signs and training videos | In case of damage to the workspace, relocate the office
| 18 | FACILITIES RISK | EXTERNAL ROBBERY |  | 1 | 4 | 4 | Safety videos | Increase surveillance and security devices in case the company is at risk of the incident happening again
| 19 | FACILITIES RISK | CYCLONE |  | 1 | 4 | 4 | Safety signs and training videos | Evacuate and follow the measures established by the government
| 20 | FACILITIES RISK | OBSOLET HARDWARE |  | 2 | 3 | 6 | Validate that the hardware that was purchased is what is needed | Buy the required hardware
| 21 | FACILITIES RISK | DEFECTIVE FACILITIES |  | 1 | 3 | 3 | Check the facilities | Repair the facilities before starting the development of the project
| 22 | FINANCIAL RISK | MONEY TRAFFIC OR THEFT |  | 1 | 4 | 4 | Monetary penalties | Take legal action
| 23 | FINANCIAL RISK | INCREASE IN TAXES |  | 3 | 4 | 12 | Fund to mitigate inflation and tax increase | Adjust costs | 50000
| 24 | FINANCIAL RISK | BREACH OF PAYMENTS |  | 1 | 4 | 4 | Check total budget | Remuneration of 3% for the breach of the company for all workers
| 25 | FINANCIAL RISK | DEVALUATION OR INFLATION OF THE CURRENCY |  | 2 | 3 | 6 | Comply with the times established in the schedule | Adjust the salary of the employees to the percentage of devaluation that is had
| 26 | TECHNICAL RISK | HACKING ATTEMPT |  | 1 | 3 | 3 | Follow the measures established for the development | Increase security so that another incident does not occur again
| 27 | TECHNICAL RISK | LICENSES NOT AUTHORIZED |  | 2 | 3 | 6 | Verify that the licenses that are necessary for development have been acquired | Pay the fine to the company and acquire the license
| 28 | TECHNICAL RISK | NO TECHNOLOGY PLAN |  | 1 | 3 | 3 | Verify that the technology plan is correct and elaborated | Prepare the technology plan based on the project
| 29 | TECHNICAL RISK | MISUSE OF TECHNOLOGIES |  | 3 | 3 | 9 | Deliver regulations to employees to prevent misuse of equipment | Punish the misuse of the development team to those who do not comply with the established agreements | 5000
| 30 | TECHNICAL RISK | EQUIPMENT FAILURE |  | 1 | 3 | 3 | Verify that the purchased equipment is in the best conditions | Make the necessary repairs and if it is not possible to acquire new equipment
| 31 | POLITICAL RISK | CHANGE OF SCOPE AND OBJECTIVES |  | 2 | 4 | 8 | Validate during the analysis stage that the scope and objectives are correct with the client. | Sign agreements to avoid change of scope and objectives in the development stage | 15000
| 32 | POLITICAL RISK | STAFF STRIKE |  | 1 | 3 | 3 | Sign agreements to avoid change of scope and objectives in the development stage | Take legal action
| 33 | POLITICAL RISK | WAR |  | 1 | 4 | 4 | Government training videos | Follow the instructions indicated by the government
| 34 | POLITICAL RISK | EXPROPRIATIONS |  | 1 | 4 | 4 | Work following the regulations and laws established by the government | Follow government instructions
| 35 | POLITICAL RISK | EXTERNAL SANCTIONS |  | 1 | 4 | 4 | Work following the regulations and laws established by the government | Follow government instructions
| 36 | DEVELOPMENT RISK | PLANNING MISTAKES (PROCESSES & TIMES) |  | 2 | 3 | 6 | Validate all documentation generated for planning | Redo the planning
| 37 | DEVELOPMENT RISK | DISABLED ANALYSIS |  | 1 | 4 | 4 | Keep the analytics team or analyst motivated | Find new staff and delegate activities to the administrator
| 38 | DEVELOPMENT RISK | HIDDEN FAILURES IN PROGRAMMING CODE AND DATA BASES |  | 2 | 4 | 8 | Deliver the complete documentation to the database team | Hire an expert who supports the database | 10000
| 39 | DEVELOPMENT RISK | TESTING FAILURES |  | 2 | 3 | 6 | Have very well established functional and non-functional requirements | Document and correct testing errors
| 40 | DEVELOPMENT RISK | IMPLEMENTATION FAILURES |  | 3 | 4 | 12 | Generate the necessary documentation to correctly carry out the implementation | Designate the developers in the implementation | 30000
| 41 | DEVELOPMENT RISK | FAILURES IN CONTRACT |  | 1 | 4 | 4 | Legally verify the contract presented | Legally resolve any discrepancy or conflict resulting from the contract
| 42 | TECHNICAL RISK | INCORRECT TIMES IN SCHEDULES |  | 1 | 3 | 3 | Check the times established in the schedule | Hire more staff so that the development of the software is in the established times
| 43 | HUMAN RESOURCES RISK | LACK OF KNOWLEDGE IN THE METHODOLOGY |  | 2 | 3 | 6 | Interview staff before being hired | Training videos
| 44 | HUMAN RESOURCES RISK | MEDIOCRE ANALYSIS |  | 2 | 4 | 8 | Verify with the clerk and with the administrator the generated S.R.S | Hire a senior analyst for support | 20000
| 45 | HUMAN RESOURCES RISK | LACK OF ORGANIZATION IN THE DEVELOPMENT TEAM |  | 2 | 3 | 6 | Training videos and supervision | Apply company regulations
| 46 | HUMAN RESOURCES RISK | INSUFFICIENT DEVELOPMENT TEAM |  | 1 | 3 | 3 | Hire the required members | Hire more trained staff
| 47 | DEVELOPMENT RISK | SUPPLIER FAILURES |  | 2 | 3 | 6 | Compromise agreements | Take legal action
[9 empty] | BUDGET | 190000